## Team Lead Checklist
SAAZA TEAM LEAD CHECKLIST
The 4-Phase SAAZA Process (Unit 4) — Marine Survey & Assault Zone Assessment
Overall progress: |  | 0 of 34 complete
PHASE 1 — INFORMATION GATHERING
Collection and consolidation of all pre-existing information on the location
Status | Task | Reference / Detail | Notes
Not Started | Pull previously completed surveys | Talon Point / Zone Availability Reports (ZARs). NIPR: talonpoint.net — best single source; shows prior areas of concern
Not Started | Obtain satellite imagery | S-2 products, Google Earth, HAWG-VIEW
Not Started | Acquire maps | Record series, sheet number, edition, and date
Not Started | Gather ATC supplemental information | Airspace, frequencies, restrictions
Not Started | Obtain weather reports | Forecast and climatology for the window
Not Started | Review intelligence reports | Threat, terrain, recent activity
Not Started | Establish Host Nation (HN) POCs | Coordination and access
Not Started | Confirm requestor criteria (T/M/S) | NATOPS-specific: glideslopes, gradients, airframe mission weight (FW), LZ size requirements, supplemental requests — your assessment depends on this
Not Started | Inventory available assets | Logistics (air/ground insert, life support for time on station), personnel (EAF integration, security), equipment
Not Started | Identify information gaps & build collection plan | Determine what you HAVE to find what you DON'T — prioritize for the site visit
PHASE 2 — PREPARATION
Team planning, task assignment, logistics (Proper Prior Planning…)
Status | Task | Reference / Detail | Notes
Not Started | Define mission requirements | LZ purpose (ALZ / HLZ / FARP), requesting agency (T/M/S), supplemental requests
Not Started | Identify limitations | Time (incl. time of day), personnel, security concerns
Not Started | Confirm available assets | Re-verify logistics, personnel, equipment for execution
Not Started | Task organization | Assign primary, secondary & tertiary tasks to every member; integrate EAF & security personnel
Not Started | Conduct mission briefing | TL paints clear, concise ground scheme of maneuver to ALL members & attachments; set output expectations
Not Started | Conduct rehearsals | Walk through tasks and contingencies
Not Started | Prepare & inventory equipment | LRF, DCP, clinometer, DAGR, line level, measuring wheel, compass, digital camera
Not Started | Plan staging | Insert/extract, sequence on site
PHASE 3 — SITE VISIT
Physical collection of ground truth data (the simplest phase — if well prepared)
Status | Task | Reference / Detail | Notes
Not Started | Confirm time available → set scope | Hasty survey/assessment < 6 hr • Full survey/assessment ≥ 12 hr
Not Started | TL supervises AND participates | Not solely a supervisor; ensure plan executed as briefed, adjust as needed
Not Started | Verify / collect coordinates | WGS-84 via DAGR; lat/long to nearest 1/1000th minute
Not Started | Measure LZ / runway dimensions | Actual ground data in feet (not minimums)
Not Started | Conduct DCP testing (CBR) | Required locations; 36 in deep; 2 personnel; ~7 min/location; prioritize touchdown, braking, turnaround, point of rotation, weak/wet/repaired areas
Not Started | Measure gradients | Longitudinal & transverse; carry +/- signs; line level (20 ft) or clinometer
Not Started | Identify obstacles & approach/departure | Glideslope ratios, radials, heights; recommended approach & departure axis; restricted quadrants
Not Started | Conduct SPACI / surface condition assessment | 8 distress types; section-by-section
Not Started | Photograph the site | Document surface, obstacles, features
Not Started | Maintain equipment accountability | At ALL times — a DCP cone is an indicator to the enemy
PHASE 4 — FINAL PRODUCT DEVELOPMENT
Synthesis of all data into a cohesive document for the requesting agency
Status | Task | Reference / Detail | Notes
Not Started | Analyze & synthesize data | CBR: identify layers, average per layer, find controlling (weakest) layer/location; gradient averages (e.g. 150 readings → 15×200 ft avgs → 1 cumulative)
Not Started | Determine allowable passes | Driven by the weakest/controlling layer
Not Started | Refine product | LZ diagram (north arrow, scale, dimensions, obstacles w/ distances & heights), photographs
Not Started | Complete survey form | AF IMT 3822 (fixed-wing / ALZ) • AF IMT 4303 (helicopter / tilt-rotor HLZ)
Not Started | Quality control review | EAF OIC / MAW Rep checks the survey
Not Started | Submit via Talon Point routing | Survey → QC (EAF OIC) → MAG ASO/MAW DOS (Safety of Flight) → MAG CO/MAW CG (Approve/Disapprove)